## Summary_DPR
Details | Links | I&C | NMS | AT | TS/ PAC | FAC/ PAC | Remarks
Phase_1 | 212 | 210 | 210 | 209 | 208/209 | 209/209 | 2 pending links cancelled
Phase_2 Roll out | 56 | 53 | 53 | 45 | 36/44 | 38/44 | Rectification in WIP for PAC pending links
Phase_2 Swap | 104+5 | 77/91 | 19 | 0 | 4/0 | 0/0 | NMS integration in Mechi on hold due to Optical link not ready & configuration issue in Huawei IPRAN

## phase-2 upperbelt
Sr. No. | Link priority | Site category | Site ID | New Link ID | Frequency | Link configuration | Site 1 ID | Old Site ID 1 | Site 1 Name | Site 2 ID | Old Site ID 2 | Site 2 Name | Site 1 type | Site 2 type | MW Ring/Spur | Hop length (Km) | Antenna size 1 (m) | Antenna size 2 (m) | I&C status | I&C completion date | ATN port No._Site 1 | ATN port No._Site 2 | NMS integration date | PAT date | PAT submitted date | PAC issue date | FAC submission date | FAC issue date | E2E MW route NMS integrated | Traffic migration completion date | Delay : NMS integration v/s Traffic migration | Traffic migration status | Issue(s) | Target date | Issue Owner | Issue solve date | Remarks
| 61 |  | 109 | 109 | 109 | 109 | 109 |  |  | 109 |  | 109 | 109 | [5 empty] | 8 | 77 | 31 | 31 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 20 |  | 14 | 2 | 22
1 | 1 | Swap | KOS011 | KOS011_MEC141_V+H | 8 GHz | 2+0 | KOS011 | KOS711 | Myanglung (terhathum) | MEC141 | MEC141 | Jingden | Outdoor | Outdoor | Spur | 12.52 | 0.6 | 0.9 |  | 2016-11-22 |  |  | 2016-12-06
2 | 1 | Swap | KOS416 | KOS022_KOS416_V+H | 7 GHz | 2+0 | KOS022 | KOS722 | Panbari | KOS416 | KOS416 | Namje (bhedetar) | Outdoor | Outdoor | Spur | 9.34 | 0.6 | 1.2 |  | 2016-08-06 | 20 | - | 2016-11-23 | [6 empty] | migrated
3 | 1 | Swap | KOs105 | KOS051_KOS105_V+H | 8 GHz | 2+0 | KOS051 | KOS751 | Dadabazar | KOS105 | KOS805 | Torkey_luhakil | Outdoor | Outdoor | Spur | 12.83 | 0.6 | 1.2 |  | 2016-11-17 | 18 | 19 | 2016-11-21 | [12 empty] | 2016-11-15
4 | 1 | Swap | MEC094 | KOS105_MEC094_V+H | 8 GHz | 2+0 | KOS105 | KOS805 | Torkey_luhakil | MEC094 | MEC094 | Mauwa | Outdoor | Outdoor | Spur | 13.48 | 0.6 | 1.2 |  | 2016-11-21 |  |  | 2016-11-21 | [12 empty] | 2016-11-15
5 | 1 | Swap | KOS191 | KOS191_KOS011_V+H | 7 GHz | 2+0 | KOS191 | KOS891 | KOS191 | KOS011 | KOS711 | Myanglung (terhathum) | Outdoor | Outdoor | Spur | 7.7 | 0.9 | 0.9 |  | 2016-11-23
6 | 1 | Swap | MEC451 | MEC094_MEC451_V | 7 GHz | 2+0 | MEC094 | MEC094 | Mauwa | MEC451 | MEC451 | Wasangu tole | Outdoor | Outdoor | Spur | 11.2 | 0.9 | 0.9 |  | 2016-11-29 |  |  | 2016-11-30
7 | 1 | Swap | KOS416 | KOS416_KOS051_V+H | 18 GHz | 2+0 | KOS416 | KOS416 | Namje (bhedetar) | KOS051 | KOS751 | Dadabazar | Outdoor | Outdoor | Spur | 5.99 | 0.6 | 0.9 |  | 2016-08-08 | 18 | 19 | 2016-11-23
8 | 1 | Swap | MEC158 | MEC158_MEC141_V+H | 8 GHz | 2+0 | MEC158 | MEC158 | MEC158 | MEC141 | MEC141 | MEC141 | Outdoor | Outdoor | Spur | 6.7 | 0.6 | 0.9 |  | 2016-11-18 |  |  | 2016-12-06
9 | 1 | Swap | MEC421 | MEC158_MEC421_V+H | 18 GHz | 2+0 | MEC158 | MEC158 | Siran tole | MEC421 | MEC1121 | Loprrekutti | Outdoor | Outdoor | Spur | 5.38 | 0.6 | 0.6 |  | 2016-11-28 | 18 | 19 | [14 empty] | NMS integration on hold due to issue in IPRAN
10 | 1 | Swap | MEC413 | MEC421_MEC413_V+H | 18 GHz | 2+0 | MEC421 | MEC1121 | Loprrekutti | MEC413 | MEC1113 | Silaute | Outdoor | Outdoor | Spur | 3.63 | 0 | 0.6 |  | 2016-09-06 | 18 | 19 | [14 empty] | NMS integration on hold due to issue in IPRAN
11 | 1 | Swap | KOS245 | KOS011_KOS245_V | 18 GHz | 1+0 | KOS011 | KOS711 | Myanglung (terhathum) | KOS245 | KOS945 | Aushidada | Outdoor | Outdoor | Spur | 6.65 | 0.6 | 0.9 |  | 2016-08-21 | BTS E0 | 18
12 | 1 | Swap | MEC107 | KOS105_MEC107_V | 8 GHz | 1+0 | KOS105 | KOS805 | Torkey_luhakil | MEC107 | MEC107 | Lekhgaon | Outdoor | Outdoor | Spur | 9.12 | 0.6 | 0.9 |  | 2016-11-26 |  |  | 2016-11-29
13 | 1 | Swap | KOS133 | KOS133_KOS105_V | 7 GHz | 1+0 | KOS133 | KOS833 | Singadevi | KOS105 | KOS805 | Torkey_luhakil | Outdoor | Outdoor | Spur | 7.24 | 0.6 | 0.9 |  | 2016-11-18 |  |  | 2016-11-21
14 | 1 | Swap | MEC141 | MEC044_MEC141_V | 18 GHz | 1+0 | MEC044 | MEC744 | Yashok | MEC141 | MEC141 | Jingden | Outdoor | Outdoor | Spur | 3.69 | 0.3 | 0.6 |  | 2016-09-06 | 18 | 19 | dec
15 | 1 | Swap | MEC044 | MEC044_MEC451_V | 18 GHz | 2+0 | MEC044 | MEC744 | Yashok | MEC451 | MEC451 | Wasangu tole | Outdoor | Outdoor | Spur | 5.35 | 0.3 | 0.6 |  | 2016-09-05 | 18 | 19 | 2016-12-05
16 | 1 | Swap | MEC096 | MEC096_MEC413_V | 8 GHz | 1+0 | MEC096 | MEC796 | Phaktep,ghurbise pancha | MEC413 | MEC1113 | Silaute | Outdoor | Outdoor | Spur | 8 | 0.3 | 0.9 |  | 2016-11-21 | [12 empty] | RSL not achieved |  |  |  | NMS integration on hold due to issue in IPRAN
17 | 1 | Swap | MEC116 | MEC116_MEC105_H | 8 GHz | 1+0 | MEC116 | MEC116 | taragaun | MEC105 | MEC105 | Chulidanda, akase | Outdoor | Outdoor | Spur | 8.65 | 0.6 | 0.6 |  | 2016-11-25 | [16 empty] | NMS integration on hold due to issue in IPRAN
18 | 1 | Swap | MEC126 | MEC126_MEC413_H | 7 GHz | 1+0 | MEC126 | MEC126 | Cheketar | MEC413 | MEC1113 | Silaute | Outdoor | Outdoor | Spur | 10.74 | 0.6 | 0.9 |  | 2016-11-15 | [16 empty] | NMS integration on hold due to issue in IPRAN
19 | 1 | Swap | MEC057 | MEC144_MEC057_V | 8 GHz | 1+0 | MEC144 | MEC144 | Gurash nagi | MEC057 | MEC757 | Kalikadevi khalangatar | Outdoor | Outdoor | Spur | 11.06 | 0.6 | 0.9 |  | 2016-11-20 | [16 empty] | NMS integration on hold due to issue in IPRAN
20 | 1 | Swap | MEC194 | MEC194_MEC105_H | 18 GHz | 1+0 | MEC194 | MEC194 | MEC194 | MEC105 | MEC105 | Chulidanda, akase | Outdoor | Outdoor | Spur | 2.27 | 0.6 | 0.3 |  | 2016-12-01 | [16 empty] | NMS integration on hold due to issue in IPRAN
21 | 1 | Swap | MEC425 | MEC413_MEC425_H | 7 GHz | 1+0 | MEC413 | MEC1113 | Silaute | MEC425 | MEC425 | Kabiredanda nagipancham | Outdoor | Outdoor | Spur | 20.14 | 1.2 | 1.2 |  | 2016-10-27 | [16 empty] | NMS integration on hold due to issue in IPRAN
22 | 1 | Swap | MEC105 | MEC421_MEC105_V | 8 GHz | 1+0 | MEC421 | MEC1121 | Loprrekutti | MEC105 | MEC105 | Chulidanda, akase | Outdoor | Outdoor | Spur | 10.34 | 0.9 | 0.9 |  | 2016-11-24 | [16 empty] | NMS integration on hold due to issue in IPRAN
23 | 1 | Swap | MEC190 | MEC425_MEC190_H | 7 GHz | 1+0 | MEC425 | MEC425 | Kabiredanda nagipancham | MEC190 | MEC190 | MEC190 | Outdoor | Outdoor | Spur | 9.97 | 0.6 | 0.6 |  | 2016-11-21 | [16 empty] | NMS integration on hold due to issue in IPRAN
24 | 2 | RO 2015 | KOS284 | KOS027_KOS284_V | 7 GHz | 1+0 | KOS027 | KOS727 | Bhojpur | KOS284 | KOS284 | KOS284 | Outdoor | Outdoor | Spur | 8.26 | 0.6 | 0.9 |  | 2016-12-01 | [12 empty] | RSL not achieved
25 | 2 | Swap | KOS069 | KOS038_KOS069_V | 7 GHz | 1+0 | KOS038 | KOS738 | Khadbari | KOS069 | KOS769 | Dangigaun | Outdoor | Outdoor | Spur | 15.87 | 0.6 | 0.6
26 | 2 | Swap | KOS038 | KOS038_KOS078_V | 8 GHz | 1+0 | KOS038 | KOS738 | Khadbari | KOS078 | KOS778 | Kafaldanda | Outdoor | Outdoor | Spur | 13.4 | 0.6 | 1.2 |  | 2016-11-16
27 | 2 | Swap | KOS212 | KOS069_KOS212_V | 18 GHz | 1+0 | KOS069 | KOS769 | Dangigaun | KOS212 | KOS912 | Kattike danda | Outdoor | Outdoor | Spur | 3.56 | 0.6 | 0.6 |  | 2016-11-15
28 | 2 | Swap | KOS078 | KOS078_KOS251_V | 18 GHz | 1+0 | KOS078 | KOS778 | Kafaldanda | KOS251 | KOS251 | Aakhibheu | Outdoor | Outdoor | Spur | 6.39 | 0.6 | 1.2 |  | 2016-11-25
29 | 2 | Swap | KOS130 | KOS130_KOS251_H | 8 GHz | 1+0 | KOS130 | KOS130 | Deurali | KOS251 | KOS251 | Aakhibheu | Outdoor | Outdoor | Spur | 11.46 | 0.6 | 0.9 |  | 2016-11-26
30 | 2 | Swap | KOS131 | KOS131_KOS171_V | 8 GHz | 1+0 | KOS131 | KOS831 | Kattidanda | KOS171 | KOS871 | Marekedanda | Outdoor | Outdoor | Spur | 11.85 | 0.6 | 0.9 |  | 2016-11-26
31 | 2 | Swap | KOS134 | KOS134_KOS131_H | 7 GHz | 1+0 | KOS134 | KOS834 | Dhilaunebote | KOS131 | KOS831 | Kattidanda | Outdoor | Outdoor | Spur | 7.9 | 0.6 | 0.9 |  | 2016-09-28
32 | 2 | Swap | KOS161 | KOS161_KOS212_V | 8 GHz | 1+0 | KOS161 | KOS161 | Bihibare | KOS212 | KOS912 | Kattike danda | Outdoor | Outdoor | Spur | 6.12 | 1.2 | 0.6 |  | 2016-11-24
33 | Hold | Swap | KOS171 | KOS171_KOS421_V | 8 GHz | 1+0 | KOS171 | KOS871 | Marekedanda | KOS421 | KOS421 | Siduwa bazaar | Outdoor | Outdoor | Spur | 8.13 | 1.2 | 0.9 | WIP | [13 empty] | Space issue at KOS421 for MW boom, Optical status of KOS421 also delayed by OFC team |  | IPRAN team |  | Space issue will be solved, once existing 1 MW links will be dismantled, after KOS421 is optically integrated.
34 | 2 | Swap | KOS172 | KOS172_KOS078_H | 8 GHz | 1+0 | KOS172 | KOS172 | Tumlingtar | KOS078 | KOS778 | Kafaldanda | Outdoor | Outdoor | Spur | 7.58 | 0.9 | 0.6 |  | 2016-11-16
35 | 2 | Swap | KOS145 | KOS191_KOS145_V | 8 GHz | 1+0 | KOS191 | KOS191 | Okhare | KOS145 | KOS845 | Sukrabare | Outdoor | Outdoor | Spur | 5.38 | 0.9 | 0.6 |  | 2016-11-23
36 | 2 | Swap | KOS246 | KOS246_KOS171_V | 8 GHz | 1+0 | KOS246 | KOS246 | Ghorlikhark | KOS171 | KOS871 | Marekedanda | Outdoor | Outdoor | Spur | 7.06 | 0.6 | 0.6 |  | 2016-10-27
37 | 2 | Swap | KOS251 | KOS251_KOS410_V | 7 GHz | 1+0 | KOS251 | KOS251 | Aakhibheu | KOS410 | KOS410 | Ganeshtar | Outdoor | Outdoor | Spur | 17.45 | 1.2 | 1.2 | WIP
38 | 2 | Swap | KOS027 | KOS268_KOS027_V | 8 GHz | 1+0 | KOS268 | KOS268 | KOS268 | KOS027 | KOS727 | Bhojpur | Outdoor | Outdoor | Spur | 8.28 | 0.9 | 0.9 |  | 2016-09-27
39 | 2 | Swap | KOS132 | KOS283_KOS132_V | 8 GHz | 1+0 | KOS283 | KOS283 | KOS283 | KOS132 | KOS132 | Suntale | Outdoor | Outdoor | Spur | 11.41 | 0.3 | 0.6 |  | 2016-12-07
40 | 2 | RO 2015 | KOS283 | KOS283_KOS268_V | 8 GHz | 1+0 | KOS283 | KOS283 | KOS283 | KOS268 | KOS268 | KOS268 | Outdoor | Outdoor | Spur | 6.71 | 0.6 | 0.6
41 | 2 | Swap | KOS134 | KOS284_KOS134_V | 7 GHz | 1+0 | KOS284 | KOS284 | KOS284 | KOS134 | KOS834 | Dhilaunebote | Outdoor | Outdoor | Spur | 11.75 | 0.6 | 0.9 |  | 2016-12-02
42 | 2 | Swap | MEC188 | MEC107_MEC188_V | 18 GHz | 1+0 | MEC107 | MEC107 | Lekhgaon | MEC188 | MEC188 | MEC188 | Outdoor | Outdoor | Spur | 4.98 | 0.6 | 0.6 |  | 2016-11-28 | [16 empty] | NMS integration on hold due to issue in IPRAN
43 |  | RO 2015 | BRN045 | BRN032_BRN045_V | 18 GHz | 1+0 | BRN032 | BRN032 | BRN032 | BRN045 | BRN045 | BRN045 | Outdoor | Outdoor | Spur | 0.71 | 0.3 | 0.3 |  | 2016-10-28 | 20 | 18 | 2016-10-28
44 |  | Swap | KOS149 | DHK001_KOS149_V | 18 GHz | 1+0 | DHK001 | KOS005 | Dhankuta | KOS149 | KOS849 | Maula dada | Outdoor | Outdoor | Spur | 6.41 | 0.3 | 0.9 |  | 2016-12-07
45 |  | Swap | KOS205 | DHK002_KOS205_V | 18 GHz | 1+0 | DHK002 | KOS412 | Hile | KOS205 | KOS205 | Bhirgau | Outdoor | Outdoor | Spur | 3.83 | 0.3 | 0.6 |  | 2016-08-14 | CX 0 | 19
46 |  | Swap | DHK003 | DHK003_KOS149_V | 8 GHz | 1+0 | DHK003 | KOS435 | Chiyanedanda | KOS149 | KOS849 | Maula dada | Outdoor | Outdoor | Spur | 6.74 | 0.3 | 0.6 |  | 2016-11-23
47 |  | Swap | KOS205 | DHK003_KOS205_V | 18 GHz | 1+0 | DHK003 | KOS435 | Chiyanedanda | KOS205 | KOS205 | Bhirgau | Outdoor | Outdoor | Spur | 3.97 | 0.6 | 0.6 |  | 2016-08-13 | 18 | 18
48 |  | Swap | KOS156 | KOS042_KOS156_V | 18 GHz | 1+0 | KOS042 | KOS042 | Pidari | KOS156 | KOS856 | Bharaul | Outdoor | Outdoor | Spur | 2.69 | 0.6 | 0.6 |  | 2016-08-12 | 18 | 18
49 |  | Swap | KOS227 | KOS051_KOS227_V | 18 GHz | 1+0 | KOS051 | KOS751 | Dadabazar | KOS227 | KOS227 | Rajarani | Outdoor | Outdoor | Spur | 4.66 | 0.6 | 0.6 |  | 2016-08-09 | 18 | 19 | 2016-10-23
50 |  | Swap | KOS052 | KOS052_DHK002_V | 7 GHz | 1+0 | KOS052 | KOS052 | Piple | DHK002 | KOS412 | Hile | Outdoor | Outdoor | Spur | 10.92 | 0.6 | 0.9 |  | 2016-09-27
51 |  | Swap | KOS061 | KOS061_KOS186_V | 7 GHz | 1+0 | KOS061 | KOS761 | Sherpa Gaun Tamphuk | KOS186 | KOS186 | Basantpur | Outdoor | Outdoor | Spur | 10.32 | 0.6 | 0.9
52 |  | Swap | KOS193 | KOS078_KOS193_V | 8 GHz | 1+0 | KOS078 | KOS778 | Kafaldanda | KOS193 | KOS193 | Salery danda | Outdoor | Outdoor | Spur | 6.86 | 0.6 | 0.6 |  | 2016-11-25
53 |  | Swap | KOS189 | KOS149_KOS189_V | 8 GHz | 1+0 | KOS149 | KOS149 | Maula Dada | KOS189 | KOS189 | Pancha kanya | Outdoor | Outdoor | Spur | 7.38 | 0.9 | 0.9 |  | 2016-11-24
54 |  | Swap | KOS150 | KOS150_KOS052_V | 8 GHz | 1+0 | KOS150 | KOS850 | Muga | KOS052 | KOS052 | Piple | Outdoor | Outdoor | Spur | 7.2 | 0.6 | 0.6 |  | 2016-11-14
55 |  | Swap | KOS079 | KOS150_KOS079_V | 18 GHz | 1+0 | KOS150 | KOS850 | Muga | KOS079 | KOS079 | Phalate | Outdoor | Outdoor | Spur | 3.54 | 0.6 | 0.6 | WIP
56 |  | Swap | KOS160 | KOS160_DHK002_V | 18 GHz | 1+0 | KOS160 | KOS860 | Pakhribas bazar | DHK002 | KOS412 | Hile | Outdoor | Outdoor | Spur | 4.59 | 1.2 | 0.6 |  | 2016-08-17 | 18 | CX 1
57 |  | Swap | KOS162 | KOS162_KOS042_V | 18 GHz | 1+0 | KOS162 | KOS162 | Mainabari Kutti | KOS042 | KOS042 | Pidari | Outdoor | Outdoor | Spur | 3.09 | 1.2 | 0.6 |  | 2016-08-13 | 18 | 19
58 |  | Swap | KOS163 | KOS163_DHK003_H | 18 GHz | 1+0 | KOS163 | KOS863 | Belara | DHK003 | KOS435 | Chiyanedanda | Outdoor | Outdoor | Spur | 4.57 | 1.2 | 0.6 |  | 2016-08-17 | 18 | 19
59 |  | Swap | KOS175 | KOS175_KOS052_V | 18 GHz | 1+0 | KOS175 | KOS875 | Sambhugaun | KOS052 | KOS052 | Piple | Outdoor | Outdoor | Spur | 4.57 | 0.9 | 0.6 |  | 2016-08-19 | 18 | 18
60 |  | Swap | KOS209 | KOS179_KOS029_V | 18 GHz | 1+0 | KOS179 | KOS179 | Salbani | KOS029 | KOS729 | Chakraghatti | Outdoor | Outdoor | Spur | 3.71 | 0.9 | 0.3 |  | 2016-08-15 | 18 | 19
61 |  | Swap | KOS413 | KOS185_KOS413_V | 18 GHz | 1+0 | KOS185 | KOS185 | KOS185 | KOS413 | KOS413 | KOS413 | Outdoor | Outdoor | Spur | 2.45 | 0.9 | 0.3 |  | 2016-09-13 |  |  | 2016-09-13
62 |  | Swap | KOS423 | KOS186_KOS423_V | 18 GHz | 1+0 | KOS186 | KOS186 | Basantpur | KOS423 | KOS1123 | Ghumaune tar_sungnam | Outdoor | Outdoor | Spur | 5.12 | 0.9 | 0.6 |  | 2016-08-17 | 18 | 18
63 | Hold | Swap | KOS195 | KOS195_KOS275_H | 18 GHz | 1+0 | KOS195 | KOS195 | Kafle | KOS275 | KOS275 | KOS275 | Outdoor | Outdoor | Spur | 2.1 | 0.3 | 0.6 | WIP
64 |  | Swap | KOS085 | KOS198_KOS085_V | 18 GHz | 1+0 | KOS198 | KOS898 | Ekrai | KOS085 | KOS085 | Simarbaan | Outdoor | Outdoor | Spur | 2.5 | 0.6 | 0.3 |  | 2016-08-12 | 21 | 18
65 |  | Swap | KOS203 | KOS203_KOS061_V | 7 GHz | 1+0 | KOS203 | KOS203 | Khatri tole | KOS061 | KOS761 | Sherpa Gaun Tamphuk | Outdoor | Outdoor | Spur | 10.09 | 0.6 | 0.9 |  | 2016-11-28
66 |  | Swap | KOS069 | KOS203_KOS069_V | 18 GHz | 1+0 | KOS203 | KOS203 | Khatri tole | KOS069 | KOS769 | Dangigaun | Outdoor | Outdoor | Spur | 4.06 | 0.6 | 0.6 |  | 2016-11-15
67 |  | Swap | KOS210 | KOS210_KOS051_V | 18 GHz | 1+0 | KOS210 | KOS210 | Maden | KOS051 | KOS751 | Dadabazar | Outdoor | Outdoor | Spur | 4.82 | 0.6 | 0.6 |  | 2016-08-10 | 18 | 19
68 |  | Swap | KOS106 | KOS210_KOS106_V | 18 GHz | 1+0 | KOS210 | KOS210 | Maden | KOS106 | KOS806 | Lalgadi thumka | Outdoor | Outdoor | Spur | 5.61 | 0.6 | 0.6 |  | 2016-08-10 | 18 | 18
69 |  | Swap | MEC115 | KOS245_MEC115_V | 8 GHz | 1+0 | KOS245 | KOS945 | Aushidada | MEC115 | MEC115 | Batisedanda | Outdoor | Outdoor | Spur | 14.16 | 0.9 | 1.2 |  | 2016-12-02 | [16 empty] | NMS integration on hold due to issue in IPRAN
70 |  | Swap | KOS056 | KOS258_KOS056_V | 8 GHz | 1+0 | KOS258 | KOS258 | KOS258 | KOS056 | KOS756 | Sitalpati | Outdoor | Outdoor | Spur | 7.32 | 1.2 | 0.9
71 |  | Swap | KOS258 | KOS258_KOS078_V | 8 GHz | 1+0 | KOS258 | KOS258 | KOS258 | KOS078 | KOS778 | Kafaldanda | Outdoor | Outdoor | Spur | 16.1 | 1.2 | 1.2
72 |  | Swap | KOS268 | KOS268_KOS150_V | 7 GHz | 1+0 | KOS268 | KOS268 | KOS268 | KOS150 | KOS850 | Muga | Outdoor | Outdoor | Spur | 24.82 | 1.2 | 1.2
73 |  | RO 2015 | KOS269 | KOS269_KOS161_V | 7 GHz | 1+0 | KOS269 | KOS269 | KOS269 | KOS161 | KOS161 | Bihibare | Outdoor | Outdoor | Spur | 19.82 | 0.9 | 1.2
74 |  | Swap | KOS270 | KOS270_KOS132_V | 18 GHz | 1+0 | KOS270 | KOS270 | KOS270 | KOS132 | KOS132 | Suntale | Outdoor | Outdoor | Spur | 3.99 | 0.9 | 0.6
75 | Hold | Swap | KOS275 | KOS275_KOS027_H | 18 GHz | 1+0 | KOS275 | KOS275 | KOS275 | KOS027 | KOS027 | KOS027 | Outdoor | Outdoor | Spur | 0.41 | 0.3 | 0.3 | WIP
76 | Hold | RO 2015 | KOS285 | KOS285_KOS056_V | 18 GHz | 1+0 | KOS285 | KOS285 | KOS285 | KOS056 | KOS756 | Sitalpati | Outdoor | Outdoor | Spur | 4.52 | 0.6 | 0.6
77 |  | Swap | KOS419 | KOS419_DHK001_V | 18 GHz | 1+0 | KOS419 | KOS1119 | Thumki danda_belara | DHK001 | KOS005 | Dhankuta | Outdoor | Outdoor | Spur | 4.13 | 0.6 | 0.6 |  | 2016-12-01 | [12 empty] | Owner issue at DHK001 |  | Ncell
78 |  | Swap | KOS418 | KOS423_KOS418_V | 18 GHz | 1+0 | KOS423 | KOS1123 | Ghumaune tar_sungnam | KOS418 | KOS1118 | Niraula gaun_jirikhimti | Outdoor | Outdoor | Spur | 5.3 | 0.6 | 0.6 |  | 2016-08-17 | 19 | 18
79 |  | Swap | KOS433 | KOS433_KOS419_V | 8 GHz | 1+0 | KOS433 | KOS1133 | Pokhari dada | KOS419 | KOS1119 | Thumki danda_belara | Outdoor | Outdoor | Spur | 5.72 | 0.6 | 0.9
80 |  | Swap | KOS437 | KOS437_KOS416_H | 18 GHz | 1+0 | KOS437 | KOS1137 | Bhedetar | KOS416 | KOS416 | Namje (bhedetar) | Outdoor | Outdoor | Spur | 2.22 | 0.6 | 0.3 |  | 2016-08-07 | 18 | 19 | 2016-10-23
81 |  | Swap | MEC118 | MEC030_MEC118_H | 18 GHz | 1+0 | MEC030 | MEC730 | MEC030 | MEC118 | MEC818 | Birendra chowk | Outdoor | Outdoor | Spur | 0.64 | 0.3 | 0.3 |  | 2016-11-09 | [12 empty] | RSL not achieved |  |  |  | NMS integration on hold due to issue in IPRAN
82 |  | Swap | MEC030 | MEC030_MEC183_H | 7 GHz | 1+0 | MEC030 | MEC730 | MEC030 | MEC183 | MEC183 | Amarpur | Outdoor | Outdoor | Spur | 10.19 | 0.3 | 0.9 | WIP
83 |  | Swap | MEC124 | MEC036_MEC124_V | 18 GHz | 1+0 | MEC036 | MEC036 | MEC036 | MEC124 | MEC124 | MEC124 | Outdoor | Outdoor | Spur | 3.99 | 0.3 | 0.6 |  | 2016-11-16 | [16 empty] | NMS integration on hold due to issue in IPRAN
84 |  | Swap | MEC036 | MEC115_MEC036_H | 18 GHz | 1+0 | MEC115 | MEC115 | Batisedanda | MEC036 | MEC736 | Phidim | Outdoor | Outdoor | Spur | 2.68 | 0.6 | 0.6 |  | 2016-09-06 | 18 | 19 | [14 empty] | NMS integration on hold due to issue in IPRAN
85 |  | Swap | MEC125 | MEC125_MEC124_V | 18 GHz | 1+0 | MEC125 | MEC125 | Lekhbasetar | MEC124 | MEC124 | Tirtya | Outdoor | Outdoor | Spur | 4.77 | 0.6 | 0.6 |  | 2016-11-16 | 18 | 19 | [14 empty] | NMS integration on hold due to issue in IPRAN
86 |  | Swap | MEC144 | MEC144_MEC124_V | 18 GHz | 1+0 | MEC144 | MEC144 | Gurash nagi | MEC124 | MEC124 | Tirtya | Outdoor | Outdoor | Spur | 5.17 | 0.6 | 0.6 |  | 2016-11-17 | 18 | 19 | [14 empty] | NMS integration on hold due to issue in IPRAN
87 | Hold | Swap | MEC144 | MEC144_MEC425_V | 18 GHz | 1+0 | MEC144 | MEC144 | Gurash nagi | MEC425 | MEC425 | Kabiredanda nagipancham | Outdoor | Outdoor | Spur | 5.7 | 0.6 | 0.6 |  |  | 18 | 19 | [10 empty] | LOS issue |  |  |  | Link re-routed
88 |  | Swap | MEC183 | MEC183_MEC193_V | 18 GHz | 1+0 | MEC183 | MEC183 | Amarpur | MEC193 | MEC193 | MEC193 | Outdoor | Outdoor | Spur | 5.12 | 0.6 | 0.6 | WIP
89 |  | Swap | MEC128 | MEC193_MEC128_V | 18 GHz | 1+0 | MEC193 | MEC193 | MEC193 | MEC128 | MEC128 | Doramba | Outdoor | Outdoor | Spur | 4.32 | 0.6 | 0.6 |  | 2016-11-14 | [16 empty] | NMS integration on hold due to issue in IPRAN
90 |  | Swap | MEC193 | MEC193_MEC425_V | 8 GHz | 1+0 | MEC193 | MEC193 | MEC193 | MEC425 | MEC425 | MEC425 | Outdoor | Outdoor | Spur | 9.51 | 0.6 | 0.9 |  | 2016-11-10 | [16 empty] | NMS integration on hold due to issue in IPRAN
91 |  | Swap | MEC198 | MEC198_MEC451_H | 18 GHz | 1+0 | MEC198 | MEC198 | MEC198 | MEC451 | MEC451 | Wasangu tole | Outdoor | Outdoor | Spur | 4.97 | 0.6 | 0.6 |  | 2016-11-29 | 18 | 19 | 2016-11-30
92 | Hold | RO 2015 | MEC221 | MEC221_MEC030_V | 18 GHz | 1+0 | MEC221 | MEC221 | MEC221 | MEC030 | MEC730 | MEC030 | Outdoor | Outdoor | Spur | 6.1 | 0 | 0.9 | WIP | [13 empty] | Motorable bridge on the way to MEC221 from Taplejung is washed away.
93 |  | Swap | MEC438 | MEC438_MEC193_H | 18 GHz | 1+0 | MEC438 | MEC438 | Kamidanda | MEC193 | MEC193 | MEC193 | Outdoor | Outdoor | Spur | 3.89 | 0 | 0.6 |  | 2016-11-14 | [12 empty] | RSL not achieved |  |  |  | NMS integration on hold due to issue in IPRAN
94 |  | Swap | SAG205 | SAG129_SAG205_V | 18 GHz | 1+0 | SAG129 | SAG129 | SAG129 | SAG205 | SAG205 | SAG205 | Outdoor | Outdoor | Spur | 2.1 | 0 | 0.3 |  | 2016-07-01 | 19 | BTS E0 | 2016-07-01 | [6 empty] | 2016-07-02
95 |  | Swap | SAG206 | SAG206_SAG129_V | 18 GHz | 1+0 | SAG206 | SAG206 | SAG206 | SAG129 | SAG129 | SAG129 | Outdoor | Outdoor | Spur | 1.85 | 0 | 0.3 |  | 2016-07-01 | BTS E0 | 20 | 2016-07-01 | [6 empty] | 2016-07-02
96 | Extra | Swap | BPR002 | BPR002_MEC224_V | 18 GHz | 1+0 | BPR001 | MEC002 | MEC002 | MEC424 | MEC424 | MEC424 | Outdoor | Outdoor | Spur | 1.94 | 0.3 | 0.3
97 | Extra | Extra | COW022 | COW022-MEC121_V | 18 GHz | 1+0 | GCOW022 | GCOW022 | GCOW022 | MEC121 | MEC121 | Kanchanzanga | Outdoor | Outdoor | Spur | 0.52 | 0.3 | 0.3 |  | 2016-11-20 |  |  | 2016-11-21
98 | Hold | RO 2011, frozen | KOS153 | KOS153_KOS433_V | 7 GHz | 1+0 | KOS153 | KOS153 | KOS153 | KOS433 | KOS1133 | Pokhari dada | Outdoor | Outdoor | Spur | - | - | - | [14 empty] | KOS153 frozen, link on hold |  | Ncell
99 | Hold | RO 2015 | KOS155 | KOS155_KOS285_V | 18 GHz | 1+0 | KOS155 | KOS155 | KOS155 | KOS285 | KOS285 | KOS285 | Outdoor | Outdoor | Spur | 5.69 | 1.2 | 0.6 | [14 empty] | KOS155 frozen, link on hold |  | Ncell
100 | Hold | RO 2016 | KOS153 | KOS175_KOS153_H | 7 GHz | 1+0 | KOS175 | KOS875 | Sambhugaun | KOS153 | KOS153 | KOS153 | Outdoor | Outdoor | Spur | - | - | - | [14 empty] | KOS153 frozen, link on hold |  | Ncell
101 | Hold | Swap | MEC128 | KOS241_MEC128_H | 7 GHz | 1+0 | KOS241 | KOS241 | KOS241 | MEC128 | MEC128 | Doramba | Outdoor | Outdoor | Spur | - | - | - | [14 empty] | KOS241 under construction |  | Ncell
102 | Hold | RO 2015 | KOS242 | KOS242_KOS241_V | 8 GHz | 1+0 | KOS242 | KOS242 | KOS242 | KOS311 | KOS241 | KOS241 | Outdoor | Outdoor | Spur | - | - | - | [14 empty] | KOS241 under construction |  | Ncell
103 | Hold | RO 2016 | KOS241 | KOS245_KOS241_V | 7 GHz | 1+0 | KOS245 | KOS945 | Aushidada | KOS311 | KOS241 | KOS241 | Outdoor | Outdoor | Spur | - | - | - | [14 empty] | KOS241 under construction |  | Ncell
104 | Hold | RO 2016 | KOS267 | KOS267_KOS130_H | 8 GHz | 1+0 | KOS267 | KOS267 | KOS267 | KOS130 | KOS130 | Deurali | Outdoor | Outdoor | Spur | 11.53 | 0.9 | 0.9 | [14 empty] | KOS267 frozen, link on hold |  | Ncell
105 | Hold | RO 2016 | KOS322 | KOS322_KOS052_V | 8 GHz | 1+0 | KOS322 | KOS256 | KOS256 | KOS052 | KOS052 | Piple | Outdoor | Outdoor | Spur | - | - | - | [14 empty] | KOS322 frozen, link on hold |  | Ncell
106 | Hold | RO 2016 | MEC214 | MEC214_MEC030_H | 8 GHz | 1+0 | MEC214 | MEC214 | MEC214 | MEC030 | MEC730 | MEC030 | Outdoor | Outdoor | Spur | 8.07 | 0.6 | 0.9 | [14 empty] | MEC214 Frozen, govt land |  | Ncell
107 | Hold | RO 2015 | MEC220 | MEC214_MEC220_H | 8 GHz | 1+0 | MEC214 | MEC214 | MEC214 | MEC220 | MEC220 | MEC220 | Outdoor | Outdoor | Spur | 6.19 | 0 | 0.6 | [14 empty] | MEC214 Frozen, govt land |  | Ncell
108 | Hold | RO 2016 | MEC215 | MEC215_MEC221_H | 8 GHz | 1+0 | MEC215 | MEC221 | MEC221 | MEC221 | MEC221 | MEC221 | Outdoor | Outdoor | Spur | 11.21 | 0 | 0.9 | [14 empty] | MEC215 frozen, Govt land |  | Ncell
109 | Hold | Swap | ILM001 | MEC217_ILM001_H | 18 GHz | 1+0 | MEC217 | MEC217 | MEC217 | ILM001 | MEC009 | MEC009 | Outdoor | Outdoor | Spur | 0.92 | 0.3 | 0.3 | [14 empty] | MEC217 under construction |  | Ncell

## Issue tracker
Sr. No. | Problem & Issue Description | Status | No. of units | No. of units received | Affected sites / Links | Start Date | Aging | Closure date | Affect of issue | NCell Remarks | Remarks | Solution
1 | NMS integration of total 20 links in Mechi to be on hold, due to : 1. Optical link not ready at KOS011, 2. IPRAN - CX also not installed at KOS011, 3. Configuration issue in IPRAN part- MEC158 onwards | Open |  |  | 20 | 2016-12-07 | 1 |  | NMS integration of 20 installed links on hold | Solution to be checked with Ncell-IPRAN team
2 | Available POE in warehouse is less than required for Project work | Partial | 42 | 40 | 1 | 2016-11-17 | 21 |  | 1 links I&C can not be completed | 10 POEs arranged from FLM team, 5 to be handed over on 02-Dec 2016 | Request to FLM for early return of alll faulty units | Try to find out the extra POE available with FLM/ from faulty reported by FLM
3 | Space issue at KOS421 | Open |  |  | 1 | 2016-11-22 | 16 |  | 1 link I&C on hold & MW ring completion on hold, dependency 18 links | KOS421 - MW link to be on hold, till optical link for KOS421 is confirmed, as per Mr. Kushal on 29 Nov | Owner- NCell Optical team
4 | Optical node confirmation required for KOS421 & DHK002 | Open |  |  | 24 | 2016-11-21 | 17 |  | 24 sites will be dependent on DHK001-KOS149 link, will have less per site b/w available | Need to follow up with Optical team | Owner- NCell Optical team
5 | DC power not available at KOS275 | Open |  |  | 2 | 2016-11-10 | 28 |  | 2 Links I&C on hold | To be updated, next week @ 01 Dec 2016 | the equipment at 2 far ends of KOS275 has been installed
6 | KOS285 under construction | Open |  |  | 1 | 2016-11-27 | 11 |  | Link on hold | To be updated, next week @ 01 Dec 2016
7 | MEC221 is not accessible, motorable bridge washed away | Open |  |  | 1 | 2016-12-05 | 3 |  | Link on hold
8 | KOS322 frozen, link on hold | Open |  |  | 1 |  |  |  | 12 Links I&C will be on hold | TSSR in progress @ 01-Dec 2016, at new location 86.977251, 26.974295
9 | KOS153 frozen, link on hold | Open |  |  | 2 |  |  |  |  | Not included in Rollout site lists | Site frozen, from RO 2011 list
10 | KOS241 under construction | Open |  |  | 2 |  |  |  |  | On Hold
11 | MEC217 under construction | Open |  |  | 1 |  |  |  |  | On Hold
12 | KOS155 frozen, link on hold | Open |  |  | 1 |  |  |  |  | Location shifted to 87.086917, 27.453639
13 | MEC214 Frozen, govt land | Open |  |  | 1 |  |  |  |  | On Hold
14 | MEC215 frozen, Govt land | Open |  |  | 2 |  |  |  |  | On Hold
15 | KOS267 frozen, link on hold | Open |  |  | 1 |  |  |  |  | On Hold
16 | NMS Integration pending | Open |  |  | 30 | 2016-08-06 |  |  | Optical nodes not ready for NMS integration | - | Installation can not be verified for correct configuration | Request for early Optical media readiness
17 | Frequency Migration, after using dummy frequency | Open |  |  | - | - | - |  | Ceragon links can not be tuned to planned frequency | Ceragon team to switch off old MW link, based on link list & plan shared by NCell, to avoid any outages | Ceragon team will switch off required old links, within 15 days from I&C completion.
18 | 10Amp MCB requirement | Closed | 80 |  | 80 | 2016-08-01 | 50 | 2016-09-20 | MW Commissioning to be on hold after Installation at 40 sites | Final approval awaited for purchase |  | Handed Over to IBN representative
19 | 16 sq. mm Grounding cable | Closed | 280 | 300 |  | 2016-08-01 |  |  |  | 300m made available from KTM ware house
20 | PVC Flexible duct pipe | Closed | 920 | 920 |  | 2016-08-01
21 | MW pole mount (Boom) | Closed | 5 | KOS105*3, KOS051*1, KOS412*1 | 5 | 2016-09-07 | 12 | 2016-09-19 | Ceragon Antenna installation can not be done for space issue | Ceragon to transport & Install the required boom from nearby available locations. | Requirement can increase as many site not accessible at present. Boom to be provided at required site/height by NCell | IBN installer is ready to install for this time. If any other requirement arises, request to arrange the boom at nearby location.
22 | Owner issue | Closed | 1 |  | DHK001 | 2016-09-06 | 70 | 2016-11-15 | All these 3 sites are optical sites, planned for CX router |  | All dependent links will be on hold for NMS integration
23 | I&C on hold due to heavy rain/ road access at 33 sites | Closed | 33 |  | 33 links, as per list in tracker |  |  |  | I&C could not be completed in 33 links | - | - | To regularly check with Local FLM team/ House owner for access
24 | KOS241 Site Frozen | Closed | 1 |  | 2 |  |  |  | I&C could not be completed in 11 links | Dependent sites re-routed
25 | KOS284 down, due to Power issue | Closed |  |  | 1 | 2016-11-17 | 21 |  | 2 Links I&C on hold |  | the equipment at 2 far ends of KOS284 has been installed
Formulas:
Aging = TODAY()-[Start Date]

## Upper belt Port Information
S. No. | Link Name | Site 1 ID | Site 1 | Source NE Role | Source Port Name | Site 2 ID | Site 2 | Sink NE Role | Sink Port Name | Link Type | Site 1 | Site 2
1 | DHK001_DHK002 | DHK001 | 0/3/0 | ASG | XGigabitEthernet0/3/0 | DHK002 | 0/3/0 | ASG | XGigabitEthernet0/3/0 | Optical | 0/3/0 | 0/3/0
2 | DHK002_KOS421 | DHK002 | 0/3/1 | ASG | XGigabitEthernet0/3/1 | KOS421 | 0/3/1 | ASG | XGigabitEthernet0/3/1 | Optical | 0/3/1 | 0/3/1
3 | KOS421_KOS410 | KOS421 | 0/3/0 | ASG | XGigabitEthernet0/3/0 | KOS410 | 0/3/0 | ASG | XGigabitEthernet0/3/0 | Optical | 0/3/0 | 0/3/0
4 | DHK001_DHR004 | DHK001 | 0/3/1 | ASG | XGigabitEthernet0/3/1 | DHR004 | 0/5/0 | ASG | XGigabitEthernet0/5/0 | Optical | 0/3/1 | 0/5/0
5 | KOS410_KOS186 | KOS410 | 0/3/1 | ASG | XGigabitEthernet0/3/1 | KOS186 | 0/3/1 | ASG | XGigabitEthernet0/3/1 | Optical | 0/3/1 | 0/3/1
6 | KOS186_KOS011 | KOS186 | 0/3/0 | ASG | XGigabitEthernet0/3/0 | KOS011 | 0/3/0 | ASG | XGigabitEthernet0/3/0 | Optical | 0/3/0 | 0/3/0
7 | ITH002_A_KOS022 | ITH002_A | 0/2/0 | ASG | GigabitEthernet0/2/0 | KOS022 | 0/1/0 | ASG | GigabitEthernet0/1/0 | MW | 0/2/0 | 0/1/0
8 | KOS022_KOS416 | KOS022 | 0/2/3 | ASG | GigabitEthernet0/2/3 | KOS416 | 0/2/3 | ASG | GigabitEthernet0/2/3 | MW | 0/2/3 | 0/2/3
9 | KOS416_KOS410 | KOS416 | 0/1/1 | ASG | GigabitEthernet0/1/1 | KOS410 | 0/1/1 | ASG | GigabitEthernet0/1/1 | MW | 0/1/1 | 0/1/1
10 | KOS419_DHK001 | KOS419 | 0/2/19 | CSG | GigabitEthernet0/2/19 | DHK001 | 0/1/0 | ASG | GigabitEthernet0/1/0 | MW | 0/2/19 | 0/1/0
11 | KOS149_DHK001 | KOS149 | 0/2/19 | CSG | GigabitEthernet0/2/19 | DHK001 | 0/2/2 | ASG | GigabitEthernet0/2/2 | MW | 0/2/19 | 0/2/2
12 | KOS052_DHK002 | KOS052 | 0/2/21 | CSG | GigabitEthernet0/2/21 | DHK002 | 0/1/0 | ASG | GigabitEthernet0/1/0 | MW | 0/2/21 | 0/1/0
13 | KOS175_KOS052 | KOS175 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS052 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
14 | DHK002_KOS160 | DHK002 | 0/1/1 | ASG | GigabitEthernet0/1/1 | KOS160 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/1/1 | 0/2/18
15 | KOS149_DHK003 | KOS149 | 0/2/18 | CSG | GigabitEthernet0/2/18 | DHK003 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
16 | KOS433_KOS419 | KOS433 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS419 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
17 | KOS433_KOS153 | KOS433 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS153 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
18 | DHK003_KOS205 | DHK003 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS205 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
19 | DHK003_KOS163 | DHK003 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS163 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
20 | DHK002_KOS205 | DHK002 | 0/2/2 | ASG | GigabitEthernet0/2/2 | KOS205 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/2 | 0/2/18
21 | KOS150_KOS052 | KOS150 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS052 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
22 | KOS256_KOS052 | KOS256 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS052 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
23 | KOS175_KOS153 | KOS175 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS153 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
24 | KOS150_KOS079 | KOS150 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS079 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
25 | KOS150_KOS268 | KOS150 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS268 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
26 | KOS268_KOS027 | KOS268 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS027 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
27 | KOS283_KOS268 | KOS283 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS268 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
28 | KOS027_KOS275 | KOS027 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS275 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
29 | KOS027_KOS284 | KOS027 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS284 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
30 | KOS284_KOS134 | KOS284 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS134 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
31 | KOS134_KOS131 | KOS134 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS131 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
32 | KOS277_KOS256 | KOS277 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS256 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
33 | KOS171_KOS131 | KOS171 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS131 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
34 | KOS171_KOS421 | KOS171 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS421 | 0/1/0 | ASG | GigabitEthernet0/1/0 | MW | 0/2/20 | 0/1/0
35 | KOS195_KOS275 | KOS195 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS275 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
36 | KOS171_KOS246 | KOS171 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS246 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
37 | KOS132_KOS270 | KOS132 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS270 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
38 | KOS132_KOS283 | KOS132 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS283 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
39 | KOS105_KOS051 | KOS105 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS051 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
40 | KOS051_KOS416 | KOS051 | 0/2/21 | CSG | GigabitEthernet0/2/21 | KOS416 | 0/1/0 | ASG | GigabitEthernet0/1/0 | MW | 0/2/21 | 0/1/0
41 | KOS011_KOS191 | KOS011 | 0/1/0 | ASG | GigabitEthernet0/1/0 | KOS191 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/1/0 | 0/2/19
42 | KOS191_MEC094 | KOS191 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC094 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
43 | MEC094_KOS105 | MEC094 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS105 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
44 | KOS106_KOS210 | KOS106 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS210 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
45 | KOS105_KOS133 | KOS105 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS133 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
46 | KOS051_KOS210 | KOS051 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS210 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
47 | KOS227_KOS051 | KOS227 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS051 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
48 | MEC107_KOS105 | MEC107 | 0/2/21 | CSG | GigabitEthernet0/2/21 | KOS105 | 0/2/21 | CSG | GigabitEthernet0/2/21 | MW | 0/2/21 | 0/2/21
49 | MEC188_MEC107 | MEC188 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC107 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
50 | KOS038_KOS069 | KOS038 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS069 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
51 | KOS203_KOS069 | KOS203 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS069 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
52 | KOS078_KOS038 | KOS078 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS038 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
53 | KOS061_KOS186 | KOS061 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS186 | 0/2/2 | ASG | GigabitEthernet0/2/2 | MW | 0/2/19 | 0/2/2
54 | KOS061_KOS203 | KOS061 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS203 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
55 | KOS251_KOS078 | KOS251 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS078 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
56 | KOS251_KOS410 | KOS251 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS410 | 0/1/0 | ASG | GigabitEthernet0/1/0 | MW | 0/2/20 | 0/1/0
57 | KOS172_KOS078 | KOS172 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS078 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
58 | KOS193_KOS078 | KOS193 | 0/2/21 | CSG | GigabitEthernet0/2/21 | KOS078 | 0/2/21 | CSG | GigabitEthernet0/2/21 | MW | 0/2/21 | 0/2/21
59 | KOS258_KOS078 | KOS258 | 0/2/22 | CSG | GigabitEthernet0/2/22 | KOS078 | 0/2/22 | CSG | GigabitEthernet0/2/22 | MW | 0/2/22 | 0/2/22
60 | KOS267_KOS130 | KOS267 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS130 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
61 | KOS155_KOS285 | KOS155 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS285 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
62 | KOS161_KOS212 | KOS161 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS212 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
63 | KOS161_KOS269 | KOS161 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS269 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
64 | KOS251_KOS130 | KOS251 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS130 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
65 | KOS212_KOS069 | KOS212 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS069 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
66 | KOS258_KOS056 | KOS258 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS056 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
67 | KOS056_KOS285 | KOS056 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS285 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
68 | KOS421_KOS189 | KOS421 | 0/1/1 | ASG | GigabitEthernet0/1/1 | KOS189 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/1/1 | 0/2/18
69 | KOS421_KOS145 | KOS421 | 0/2/2 | ASG | GigabitEthernet0/2/2 | KOS145 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/2 | 0/2/18
70 | KOS416_KOS437 | KOS416 | 0/2/2 | ASG | GigabitEthernet0/2/2 | KOS437 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/2 | 0/2/18
71 | MEC413_MEC096 | MEC413 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC096 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
72 | MEC413_MEC126 | MEC413 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC126 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
73 | KOS241_KOS242 | KOS241 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS242 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
74 | KOS245_KOS011 | KOS245 | 0/2/20 | CSG | GigabitEthernet0/2/20 | KOS011 | 0/1/1 | ASG | GigabitEthernet0/1/1 | MW | 0/2/20 | 0/1/1
75 | KOS241_KOS245 | KOS241 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS245 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
76 | MEC115_KOS245 | MEC115 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS245 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
77 | MEC214_MEC030 | MEC214 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC030 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
78 | MEC030_MEC221 | MEC030 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC221 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
79 | MEC036_MEC115 | MEC036 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC115 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
80 | MEC118_MEC030 | MEC118 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MEC030 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
81 | KOS241_MEC128 | KOS241 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MEC128 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
82 | MEC189_MEC128 | MEC189 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC128 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
83 | MEC128_MEC193 | MEC128 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC193 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
84 | MEC183_MEC030 | MEC183 | 0/2/21 | CSG | GigabitEthernet0/2/21 | MEC030 | 0/2/21 | CSG | GigabitEthernet0/2/21 | MW | 0/2/21 | 0/2/21
85 | MEC183_MEC193 | MEC183 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC193 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
86 | MEC220_MEC214 | MEC220 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC214 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
87 | MEC215_MEC221 | MEC215 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC221 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
88 | MEC438_MEC193 | MEC438 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MEC193 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
89 | MEC105_MEC116 | MEC105 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC116 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
90 | MEC194_MEC105 | MEC194 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC105 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
91 | MEC421_MEC105 | MEC421 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MEC105 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
92 | MEC158_MEC421 | MEC158 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC421 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
93 | MEC421_MEC413 | MEC421 | 0/2/21 | CSG | GigabitEthernet0/2/21 | MEC413 | 0/2/21 | CSG | GigabitEthernet0/2/21 | MW | 0/2/21 | 0/2/21
94 | KOS423_KOS186 | KOS423 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS186 | 0/1/0 | ASG | GigabitEthernet0/1/0 | MW | 0/2/19 | 0/1/0
95 | KOS418_KOS423 | KOS418 | 0/2/18 | CSG | GigabitEthernet0/2/18 | KOS423 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
96 | MEC124_MEC125 | MEC124 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC125 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
97 | MEC144_MEC057 | MEC144 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC057 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
98 | MEC124_MEC144 | MEC124 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC144 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
99 | MEC144_MEC425 | MEC144 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MEC425 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20
100 | MEC190_MEC163 | MEC190 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC163 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
101 | MEC190_MEC425 | MEC190 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC425 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
102 | MEC425_MEC413 | MEC425 | 0/2/22 | CSG | GigabitEthernet0/2/22 | MEC413 | 0/2/22 | CSG | GigabitEthernet0/2/22 | MW | 0/2/22 | 0/2/22
103 | MEC141_KOS011 | MEC141 | 0/2/19 | CSG | GigabitEthernet0/2/19 | KOS011 | 0/2/2 | ASG | GigabitEthernet0/2/2 | MW | 0/2/19 | 0/2/2
104 | MEC044_MEC141 | MEC044 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC141 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
105 | MEC198_MEC451 | MEC198 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MEC451 | 0/2/18 | CSG | GigabitEthernet0/2/18 | MW | 0/2/18 | 0/2/18
106 | MEC451_MEC044 | MEC451 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MEC044 | 0/2/19 | CSG | GigabitEthernet0/2/19 | MW | 0/2/19 | 0/2/19
107 | KOS410_MEC413 | KOS410 | 0/2/2 | ASG | GigabitEthernet0/2/2 | MEC413 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/2 | 0/2/20
108 | MEC094_MEC126 | MEC094 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MEC126 | 0/2/20 | CSG | GigabitEthernet0/2/20 | MW | 0/2/20 | 0/2/20

## Sheet1
S.N. | Phase | Sub Con | Route no. | Link ID (A-B) | Verify with U2000(NMS) | VLAN ID | Network IP | Network MASK | Router Port IP Site A | Router Port IP MASK | Router port at Site A | Router Port at Site B | MW Site ID - A | MW SiteA - IP | MW Site ID - B | MW SiteB IP | MW MASK Site A & B | MW Default Gateway A & B | Remarks | Status
|  |  |  | 107 |  |  | 107 | 107 | 107 | 107 |  |  | 107 | 107 | 107 | 107 | 107 | 107 | 0 | 0
1 | Upper Belt |  |  | KOS437-KOS416 |  | 2000 | 10.7.41.88 | 255.255.255.248 | 10.7.41.89 | 255.255.255.248 |  |  | KOS437 | 10.7.41.90 | KOS416 | 10.7.41.91 | 255.255.255.248 | 10.7.41.89
2 | Upper Belt |  |  | KOS416-KOS051 |  | 2000 | 10.7.41.96 | 255.255.255.248 | 10.7.41.97 | 255.255.255.248 |  |  | KOS416 | 10.7.41.98 | KOS051 | 10.7.41.99 | 255.255.255.248 | 10.7.41.97
3 | Upper Belt |  |  | KOS051-KOS227 |  | 2000 | 10.7.41.104 | 255.255.255.248 | 10.7.41.105 | 255.255.255.248 |  |  | KOS051 | 10.7.41.106 | KOS227 | 10.7.41.107 | 255.255.255.248 | 10.7.41.105
4 | Upper Belt |  |  | KOS210-KOS051 |  | 2000 | 10.7.41.112 | 255.255.255.248 | 10.7.41.113 | 255.255.255.248 |  |  | KOS210 | 10.7.41.114 | KOS051 | 10.7.41.115 | 255.255.255.248 | 10.7.41.113
5 | Upper Belt |  |  | KOS210-KOS106 |  | 2000 | 10.7.41.8 | 255.255.255.248 | 10.7.41.9 | 255.255.255.248 |  |  | KOS210 | 10.7.41.10 | KOS106 | 10.7.41.11 | 255.255.255.248 | 10.7.41.9
6 | Upper Belt |  |  | KOS198-KOS085 |  | 2000 | 10.7.41.80 | 255.255.255.248 | 10.7.41.81 | 255.255.255.248 |  |  | KOS198 | 10.7.41.82 | KOS085 | 10.7.41.83 | 255.255.255.248 | 10.7.41.81
7 | Upper Belt |  |  | DHK001-KOS149 |  | 2000 | 10.7.41.120 | 255.255.255.248 | 10.7.41.121 | 255.255.255.248 |  |  | DHK001 | 10.7.41.122 | KOS149 | 10.7.41.123 | 255.255.255.248 | 10.7.41.121
8 | Upper Belt |  |  | KOS419-DHK001 |  | 2000 | 10.7.41.128 | 255.255.255.248 | 10.7.41.129 | 255.255.255.248 |  |  | KOS419 | 10.7.41.130 | DHK001 | 10.7.41.131 | 255.255.255.248 | 10.7.41.129
9 | Upper Belt |  |  | KOS175-KOS052 |  | 2000 | 10.7.41.136 | 255.255.255.248 | 10.7.41.137 | 255.255.255.248 |  |  | KOS175 | 10.7.41.138 | KOS052 | 10.7.41.139 | 255.255.255.248 | 10.7.41.137
10 | Upper Belt |  |  | DHK003-KOS205 |  | 2000 | 10.7.41.144 | 255.255.255.248 | 10.7.41.145 | 255.255.255.248 |  |  | DHK003 | 10.7.41.146 | KOS205 | 10.7.41.147 | 255.255.255.248 | 10.7.41.145
11 | Upper Belt |  |  | DHK002-KOS205 |  | 2000 | 10.7.41.152 | 255.255.255.248 | 10.7.41.153 | 255.255.255.248 |  |  | DHK002 | 10.7.41.154 | KOS205 | 10.7.41.155 | 255.255.255.248 | 10.7.41.153
12 | Upper Belt |  |  | KOS163-DHK003 |  | 2000 | 10.7.41.160 | 255.255.255.248 | 10.7.41.161 | 255.255.255.248 |  |  | KOS163 | 10.7.41.162 | DHK003 | 10.7.41.163 | 255.255.255.248 | 10.7.41.161
13 | Upper Belt |  |  | KOS160-DHK002 |  | 2000 | 10.7.41.168 | 255.255.255.248 | 10.7.41.169 | 255.255.255.248 |  |  | KOS160 | 10.7.41.170 | DHK002 | 10.7.41.171 | 255.255.255.248 | 10.7.41.169
14 | Upper Belt |  |  | KOS150-KOS079 |  | 2000 | 10.7.41.176 | 255.255.255.248 | 10.7.41.177 | 255.255.255.248 |  |  | KOS150 | 10.7.41.178 | KOS079 | 10.7.41.179 | 255.255.255.248 | 10.7.41.177
15 | Upper Belt |  |  | KOS069-KOS212 |  | 2000 | 10.7.41.184 | 255.255.255.248 | 10.7.41.185 | 255.255.255.248 |  |  | KOS069 | 10.7.41.186 | KOS212 | 10.7.41.187 | 255.255.255.248 | 10.7.41.185
16 | Upper Belt |  |  | KOS195-KOS275 |  | 2000 | 10.7.41.192 | 255.255.255.248 | 10.7.41.193 | 255.255.255.248 |  |  | KOS195 | 10.7.41.194 | KOS275 | 10.7.41.195 | 255.255.255.248 | 10.7.41.193
17 | Upper Belt |  |  | KOS203-KOS069 |  | 2000 | 10.7.41.200 | 255.255.255.248 | 10.7.41.201 | 255.255.255.248 |  |  | KOS203 | 10.7.41.202 | KOS069 | 10.7.41.203 | 255.255.255.248 | 10.7.41.201
18 | Upper Belt |  |  | KOS078-KOS251 |  | 2000 | 10.7.41.208 | 255.255.255.248 | 10.7.41.209 | 255.255.255.248 |  |  | KOS078 | 10.7.41.210 | KOS251 | 10.7.41.211 | 255.255.255.248 | 10.7.41.209
19 | Upper Belt |  |  | KOS270-KOS132 |  | 2000 | 10.7.41.216 | 255.255.255.248 | 10.7.41.217 | 255.255.255.248 |  |  | KOS270 | 10.7.41.218 | KOS132 | 10.7.41.219 | 255.255.255.248 | 10.7.41.217
20 | Upper Belt |  |  | KOS186-KOS423 |  | 2000 | 10.7.41.224 | 255.255.255.248 | 10.7.41.225 | 255.255.255.248 |  |  | KOS186 | 10.7.41.226 | KOS423 | 10.7.41.227 | 255.255.255.248 | 10.7.41.225
21 | Upper Belt |  |  | KOS423-KOS418 |  | 2000 | 10.7.41.232 | 255.255.255.248 | 10.7.41.233 | 255.255.255.248 |  |  | KOS423 | 10.7.41.234 | KOS418 | 10.7.41.235 | 255.255.255.248 | 10.7.41.233
22 | Upper Belt |  |  | MEC198-MEC451 |  | 2000 | 10.7.41.240 | 255.255.255.248 | 10.7.41.241 | 255.255.255.248 |  |  | MEC198 | 10.7.41.242 | MEC451 | 10.7.41.243 | 255.255.255.248 | 10.7.41.241
23 | Upper Belt |  |  | MEC044-MEC451 |  | 2000 | 10.7.41.248 | 255.255.255.248 | 10.7.41.249 | 255.255.255.248 |  |  | MEC044 | 10.7.41.250 | MEC451 | 10.7.41.251 | 255.255.255.248 | 10.7.41.249
24 | Upper Belt |  |  | MEC044-MEC141 |  | 2000 | 10.7.42.0 | 255.255.255.248 | 10.7.42.1 | 255.255.255.248 |  |  | MEC044 | 10.7.42.2 | MEC141 | 10.7.42.3 | 255.255.255.248 | 10.7.42.1
25 | Upper Belt |  |  | KOS011-KOS245 |  | 2000 | 10.7.42.8 | 255.255.255.248 | 10.7.42.9 | 255.255.255.248 |  |  | KOS011 | 10.7.42.10 | KOS245 | 10.7.42.11 | 255.255.255.248 | 10.7.42.9
26 | Upper Belt |  |  | MEC421-MEC413 |  | 2000 | 10.7.42.16 | 255.255.255.248 | 10.7.42.17 | 255.255.255.248 |  |  | MEC421 | 10.7.42.18 | MEC413 | 10.7.42.19 | 255.255.255.248 | 10.7.42.17
27 | Upper Belt |  |  | MEC194-MEC105 |  | 2000 | 10.7.42.24 | 255.255.255.248 | 10.7.42.25 | 255.255.255.248 |  |  | MEC194 | 10.7.42.26 | MEC105 | 10.7.42.27 | 255.255.255.248 | 10.7.42.25
28 | Upper Belt |  |  | MEC144-MEC425 |  | 2000 | 10.7.42.32 | 255.255.255.248 | 10.7.42.33 | 255.255.255.248 |  |  | MEC144 | 10.7.42.34 | MEC425 | 10.7.42.35 | 255.255.255.248 | 10.7.42.33
29 | Upper Belt |  |  | MEC158-MEC421 |  | 2000 | 10.7.42.40 | 255.255.255.248 | 10.7.42.41 | 255.255.255.248 |  |  | MEC158 | 10.7.42.42 | MEC421 | 10.7.42.43 | 255.255.255.248 | 10.7.42.41
30 | Upper Belt |  |  | MEC115-MEC036 |  | 2000 | 10.7.42.48 | 255.255.255.248 | 10.7.42.49 | 255.255.255.248 |  |  | MEC115 | 10.7.42.50 | MEC036 | 10.7.42.51 | 255.255.255.248 | 10.7.42.49
31 | Upper Belt |  |  | MEC125-MEC124 |  | 2000 | 10.7.42.56 | 255.255.255.248 | 10.7.42.57 | 255.255.255.248 |  |  | MEC125 | 10.7.42.58 | MEC124 | 10.7.42.59 | 255.255.255.248 | 10.7.42.57
32 | Upper Belt |  |  | MEC144-MEC124 |  | 2000 | 10.7.42.64 | 255.255.255.248 | 10.7.42.65 | 255.255.255.248 |  |  | MEC144 | 10.7.42.66 | MEC124 | 10.7.42.67 | 255.255.255.248 | 10.7.42.65
33 | Upper Belt |  |  | MEC438-MEC193 |  | 2000 | 10.7.42.72 | 255.255.255.248 | 10.7.42.73 | 255.255.255.248 |  |  | MEC438 | 10.7.42.74 | MEC193 | 10.7.42.75 | 255.255.255.248 | 10.7.42.73
34 | Upper Belt |  |  | MEC193-MEC128 |  | 2000 | 10.7.42.80 | 255.255.255.248 | 10.7.42.81 | 255.255.255.248 |  |  | MEC193 | 10.7.42.82 | MEC128 | 10.7.42.83 | 255.255.255.248 | 10.7.42.81
35 | Upper Belt |  |  | MEC183-MEC193 |  | 2000 | 10.7.42.88 | 255.255.255.248 | 10.7.42.89 | 255.255.255.248 |  |  | MEC183 | 10.7.42.90 | MEC193 | 10.7.42.91 | 255.255.255.248 | 10.7.42.89
36 | Upper Belt |  |  | KOS042-KOS156 |  | 2000 | 10.7.42.96 | 255.255.255.248 | 10.7.42.97 | 255.255.255.248 |  |  | KOS042 | 10.7.42.98 | KOS156 | 10.7.42.99 | 255.255.255.248 | 10.7.42.97
37 | Upper Belt |  |  | KOS162-KOS042 |  | 2000 | 10.7.42.104 | 255.255.255.248 | 10.7.42.105 | 255.255.255.248 |  |  | KOS162 | 10.7.42.106 | KOS042 | 10.7.42.107 | 255.255.255.248 | 10.7.42.105
38 | Upper Belt |  |  | KOS179-KOS029 |  | 2000 | 10.7.42.112 | 255.255.255.248 | 10.7.42.113 | 255.255.255.248 |  |  | KOS179 | 10.7.42.114 | KOS029 | 10.7.42.115 | 255.255.255.248 | 10.7.42.113
39 | Upper Belt |  |  | MEC217-ILM001 |  | 2000 | 10.7.42.120 | 255.255.255.248 | 10.7.42.121 | 255.255.255.248 |  |  | MEC217 | 10.7.42.122 | ILM001 | 10.7.42.123 | 255.255.255.248 | 10.7.42.121
40 | Upper Belt |  |  | DHK003-KOS149 |  | 2000 | 10.7.42.128 | 255.255.255.248 | 10.7.42.129 | 255.255.255.248 |  |  | DHK003 | 10.7.42.130 | KOS149 | 10.7.42.131 | 255.255.255.248 | 10.7.42.129
41 | Upper Belt |  |  | KOS433-KOS419 |  | 2000 | 10.7.42.136 | 255.255.255.248 | 10.7.42.137 | 255.255.255.248 |  |  | KOS433 | 10.7.42.138 | KOS419 | 10.7.42.139 | 255.255.255.248 | 10.7.42.137
42 | Upper Belt |  |  | KOS246-KOS171 |  | 2000 | 10.7.42.144 | 255.255.255.248 | 10.7.42.145 | 255.255.255.248 |  |  | KOS246 | 10.7.42.146 | KOS171 | 10.7.42.147 | 255.255.255.248 | 10.7.42.145
43 | Upper Belt |  |  | KOS171-KOS421 |  | 2000 | 10.7.42.152 | 255.255.255.248 | 10.7.42.153 | 255.255.255.248 |  |  | KOS171 | 10.7.42.154 | KOS421 | 10.7.42.155 | 255.255.255.248 | 10.7.42.153
44 | Upper Belt |  |  | KOS256-KOS052 |  | 2000 | 10.7.42.160 | 255.255.255.248 | 10.7.42.161 | 255.255.255.248 |  |  | KOS256 | 10.7.42.162 | KOS052 | 10.7.42.163 | 255.255.255.248 | 10.7.42.161
45 | Upper Belt |  |  | KOS052-DHK002 |  | 2000 | 10.7.42.168 | 255.255.255.248 | 10.7.42.169 | 255.255.255.248 |  |  | KOS052 | 10.7.42.170 | DHK002 | 10.7.42.171 | 255.255.255.248 | 10.7.42.169
46 | Upper Belt |  |  | KOS268-KOS027 |  | 2000 | 10.7.42.176 | 255.255.255.248 | 10.7.42.177 | 255.255.255.248 |  |  | KOS268 | 10.7.42.178 | KOS027 | 10.7.42.179 | 255.255.255.248 | 10.7.42.177
47 | Upper Belt |  |  | KOS268-KOS150 |  | 2000 | 10.7.42.184 | 255.255.255.248 | 10.7.42.185 | 255.255.255.248 |  |  | KOS268 | 10.7.42.186 | KOS150 | 10.7.42.187 | 255.255.255.248 | 10.7.42.185
48 | Upper Belt |  |  | KOS027-KOS284 |  | 2000 | 10.7.42.192 | 255.255.255.248 | 10.7.42.193 | 255.255.255.248 |  |  | KOS027 | 10.7.42.194 | KOS284 | 10.7.42.195 | 255.255.255.248 | 10.7.42.193
49 | Upper Belt |  |  | KOS150-KOS052 |  | 2000 | 10.7.42.200 | 255.255.255.248 | 10.7.42.201 | 255.255.255.248 |  |  | KOS150 | 10.7.42.202 | KOS052 | 10.7.42.203 | 255.255.255.248 | 10.7.42.201
50 | Upper Belt |  |  | KOS153-KOS433 |  | 2000 | 10.7.42.208 | 255.255.255.248 | 10.7.42.209 | 255.255.255.248 |  |  | KOS153 | 10.7.42.210 | KOS433 | 10.7.42.211 | 255.255.255.248 | 10.7.42.209
51 | Upper Belt |  |  | KOS421-KOS189 |  | 2000 | 10.7.42.216 | 255.255.255.248 | 10.7.42.217 | 255.255.255.248 |  |  | KOS421 | 10.7.42.218 | KOS189 | 10.7.42.219 | 255.255.255.248 | 10.7.42.217
52 | Upper Belt |  |  | KOS175-KOS153 |  | 2000 | 10.7.42.224 | 255.255.255.248 | 10.7.42.225 | 255.255.255.248 |  |  | KOS175 | 10.7.42.226 | KOS153 | 10.7.42.227 | 255.255.255.248 | 10.7.42.225
53 | Upper Belt |  |  | KOS421-KOS145 |  | 2000 | 10.7.42.232 | 255.255.255.248 | 10.7.42.233 | 255.255.255.248 |  |  | KOS421 | 10.7.42.234 | KOS145 | 10.7.42.235 | 255.255.255.248 | 10.7.42.233
54 | Upper Belt |  |  | KOS134-KOS131 |  | 2000 | 10.7.42.240 | 255.255.255.248 | 10.7.42.242 | 255.255.255.248 |  |  | KOS134 | 10.7.42.242 | KOS131 | 10.7.42.243 | 255.255.255.248 | 10.7.42.242
55 | Upper Belt |  |  | KOS284-KOS134 |  | 2000 | 10.7.42.248 | 255.255.255.248 | 10.7.42.249 | 255.255.255.248 |  |  | KOS284 | 10.7.42.250 | KOS134 | 10.7.42.251 | 255.255.255.248 | 10.7.42.249
56 | Upper Belt |  |  | KOS131-KOS171 |  | 2000 | 10.7.43.0 | 255.255.255.248 | 10.7.43.1 | 255.255.255.248 |  |  | KOS131 | 10.7.43.2 | KOS171 | 10.7.43.3 | 255.255.255.248 | 10.7.43.1
57 | Upper Belt |  |  | KOS061-KOS186 |  | 2000 | 10.7.43.8 | 255.255.255.248 | 10.7.43.9 | 255.255.255.248 |  |  | KOS061 | 10.7.43.10 | KOS186 | 10.7.43.11 | 255.255.255.248 | 10.7.43.9
58 | Upper Belt |  |  | KOS251-KOS410 |  | 2000 | 10.7.43.16 | 255.255.255.248 | 10.7.43.17 | 255.255.255.248 |  |  | KOS251 | 10.7.43.18 | KOS410 | 10.7.43.19 | 255.255.255.248 | 10.7.43.17
59 | Upper Belt |  |  | KOS130-KOS251 |  | 2000 | 10.7.43.24 | 255.255.255.248 | 10.7.43.25 | 255.255.255.248 |  |  | KOS130 | 10.7.43.26 | KOS251 | 10.7.43.27 | 255.255.255.248 | 10.7.43.25
60 | Upper Belt |  |  | KOS269-KOS161 |  | 2000 | 10.7.43.32 | 255.255.255.248 | 10.7.43.33 | 255.255.255.248 |  |  | KOS269 | 10.7.43.34 | KOS161 | 10.7.43.35 | 255.255.255.248 | 10.7.43.33
61 | Upper Belt |  |  | KOS161-KOS212 |  | 2000 | 10.7.43.40 | 255.255.255.248 | 10.7.43.41 | 255.255.255.248 |  |  | KOS161 | 10.7.43.42 | KOS212 | 10.7.43.43 | 255.255.255.248 | 10.7.43.41
62 | Upper Belt |  |  | KOS285-KOS056 |  | 2000 | 10.7.43.48 | 255.255.255.248 | 10.7.43.49 | 255.255.255.248 |  |  | KOS285 | 10.7.43.50 | KOS056 | 10.7.43.51 | 255.255.255.248 | 10.7.43.49
63 | Upper Belt |  |  | KOS258-KOS056 |  | 2000 | 10.7.43.56 | 255.255.255.248 | 10.7.43.57 | 255.255.255.248 |  |  | KOS258 | 10.7.43.58 | KOS056 | 10.7.43.59 | 255.255.255.248 | 10.7.43.57
64 | Upper Belt |  |  | KOS203-KOS061 |  | 2000 | 10.7.43.64 | 255.255.255.248 | 10.7.43.65 | 255.255.255.248 |  |  | KOS203 | 10.7.43.66 | KOS061 | 10.7.43.67 | 255.255.255.248 | 10.7.43.65
65 | Upper Belt |  |  | KOS155-KOS285 |  | 2000 | 10.7.43.72 | 255.255.255.248 | 10.7.43.73 | 255.255.255.248 |  |  | KOS155 | 10.7.43.74 | KOS285 | 10.7.43.75 | 255.255.255.248 | 10.7.43.73
66 | Upper Belt |  |  | KOS078-KOS193 |  | 2000 | 10.7.43.80 | 255.255.255.248 | 10.7.43.81 | 255.255.255.248 |  |  | KOS078 | 10.7.43.82 | KOS193 | 10.7.43.83 | 255.255.255.248 | 10.7.43.81
67 | Upper Belt |  |  | KOS258-KOS078 |  | 2000 | 10.7.43.88 | 255.255.255.248 | 10.7.43.89 | 255.255.255.248 |  |  | KOS258 | 10.7.43.90 | KOS078 | 10.7.43.91 | 255.255.255.248 | 10.7.43.89
68 | Upper Belt |  |  | KOS172-KOS078 |  | 2000 | 10.7.43.96 | 255.255.255.248 | 10.7.43.97 | 255.255.255.248 |  |  | KOS172 | 10.7.43.98 | KOS078 | 10.7.43.99 | 255.255.255.248 | 10.7.43.97
69 | Upper Belt |  |  | KOS038-KOS069 |  | 2000 | 10.7.43.104 | 255.255.255.248 | 10.7.43.105 | 255.255.255.248 |  |  | KOS038 | 10.7.43.106 | KOS069 | 10.7.43.107 | 255.255.255.248 | 10.7.43.105
70 | Upper Belt |  |  | KOS038-KOS078 |  | 2000 | 10.7.43.112 | 255.255.255.248 | 10.7.43.113 | 255.255.255.248 |  |  | KOS038 | 10.7.43.114 | KOS078 | 10.7.43.115 | 255.255.255.248 | 10.7.43.113
71 | Upper Belt |  |  | KOS022-KOS416 |  | 2000 | 10.7.43.120 | 255.255.255.248 | 10.7.43.121 | 255.255.255.248 |  |  | KOS022 | 10.7.43.122 | KOS416 | 10.7.43.123 | 255.255.255.248 | 10.7.43.121
72 | Upper Belt |  |  | MEC107-MEC188 |  | 2000 | 10.7.43.128 | 255.255.255.248 | 10.7.43.129 | 255.255.255.248 |  |  | MEC107 | 10.7.43.130 | MEC188 | 10.7.43.131 | 255.255.255.248 | 10.7.43.129
73 | Upper Belt |  |  | KOS105-MEC107 |  | 2000 | 10.7.43.136 | 255.255.255.248 | 10.7.43.137 | 255.255.255.248 |  |  | KOS105 | 10.7.43.138 | MEC107 | 10.7.43.139 | 255.255.255.248 | 10.7.43.137
74 | Upper Belt |  |  | KOS241-MEC128 |  | 2000 | 10.7.43.144 | 255.255.255.248 | 10.7.43.145 | 255.255.255.248 |  |  | KOS241 | 10.7.43.146 | MEC128 | 10.7.43.147 | 255.255.255.248 | 10.7.43.145
75 | Upper Belt |  |  | MEC214-MEC030 |  | 2000 | 10.7.43.152 | 255.255.255.248 | 10.7.43.153 | 255.255.255.248 |  |  | MEC214 | 10.7.43.154 | MEC030 | 10.7.43.155 | 255.255.255.248 | 10.7.43.153
76 | Upper Belt |  |  | MEC221-MEC030 |  | 2000 | 10.7.43.160 | 255.255.255.248 | 10.7.43.161 | 255.255.255.248 |  |  | MEC221 | 10.7.43.162 | MEC030 | 10.7.43.163 | 255.255.255.248 | 10.7.43.161
77 | Upper Belt |  |  | MEC214-MEC220 |  | 2000 | 10.7.43.168 | 255.255.255.248 | 10.7.43.169 | 255.255.255.248 |  |  | MEC214 | 10.7.43.170 | MEC220 | 10.7.43.171 | 255.255.255.248 | 10.7.43.169
78 | Upper Belt |  |  | MEC030-MEC183 |  | 2000 | 10.7.43.176 | 255.255.255.248 | 10.7.43.177 | 255.255.255.248 |  |  | MEC030 | 10.7.43.178 | MEC183 | 10.7.43.179 | 255.255.255.248 | 10.7.43.177
79 | Upper Belt |  |  | KOS011-MEC141 |  | 2000 | 10.7.43.184 | 255.255.255.248 | 10.7.43.185 | 255.255.255.248 |  |  | KOS011 | 10.7.43.186 | MEC141 | 10.7.43.187 | 255.255.255.248 | 10.7.43.185
80 | Upper Belt |  |  | KOS245-KOS241 |  | 2000 | 10.7.43.192 | 255.255.255.248 | 10.7.43.193 | 255.255.255.248 |  |  | KOS245 | 10.7.43.194 | KOS241 | 10.7.43.195 | 255.255.255.248 | 10.7.43.193
81 | Upper Belt |  |  | KOS105-MEC094 |  | 2000 | 10.7.43.200 | 255.255.255.248 | 10.7.43.201 | 255.255.255.248 |  |  | KOS105 | 10.7.43.202 | MEC094 | 10.7.43.203 | 255.255.255.248 | 10.7.43.201
82 | Upper Belt |  |  | KOS051-KOS105 |  | 2000 | 10.7.43.208 | 255.255.255.248 | 10.7.43.209 | 255.255.255.248 |  |  | KOS051 | 10.7.43.210 | KOS105 | 10.7.43.211 | 255.255.255.248 | 10.7.43.209
83 | Upper Belt |  |  | KOS245-MEC115 |  | 2000 | 10.7.43.216 | 255.255.255.248 | 10.7.43.217 | 255.255.255.248 |  |  | KOS245 | 10.7.43.218 | MEC115 | 10.7.43.219 | 255.255.255.248 | 10.7.43.217
84 | Upper Belt |  |  | KOS242-KOS241 |  | 2000 | 10.7.43.224 | 255.255.255.248 | 10.7.43.225 | 255.255.255.248 |  |  | KOS242 | 10.7.43.226 | KOS241 | 10.7.43.227 | 255.255.255.248 | 10.7.43.225
85 | Upper Belt |  |  | KOS191-MEC094 |  | 2000 | 10.7.43.232 | 255.255.255.248 | 10.7.43.233 | 255.255.255.248 |  |  | KOS191 | 10.7.43.234 | MEC094 | 10.7.43.235 | 255.255.255.248 | 10.7.43.233
86 | Upper Belt |  |  | KOS191-KOS011 |  | 2000 | 10.7.43.240 | 255.255.255.248 | 10.7.43.241 | 255.255.255.248 |  |  | KOS191 | 10.7.43.242 | KOS011 | 10.7.43.243 | 255.255.255.248 | 10.7.43.241
87 | Upper Belt |  |  | KOS133-KOS105 |  | 2000 | 10.7.43.248 | 255.255.255.248 | 10.7.43.249 | 255.255.255.248 |  |  | KOS133 | 10.7.43.250 | KOS105 | 10.7.43.251 | 255.255.255.248 | 10.7.43.249
88 | Upper Belt |  |  | MEC030-MEC118 |  | 2000 | 10.7.44.0 | 255.255.255.248 | 10.7.44.1 | 255.255.255.248 |  |  | MEC030 | 10.7.44.2 | MEC118 | 10.7.44.3 | 255.255.255.248 | 10.7.44.1
89 | Upper Belt |  |  | MEC413-MEC425 |  | 2000 | 10.7.44.8 | 255.255.255.248 | 10.7.44.9 | 255.255.255.248 |  |  | MEC413 | 10.7.44.10 | MEC425 | 10.7.44.11 | 255.255.255.248 | 10.7.44.9
90 | Upper Belt |  |  | MEC421-MEC105 |  | 2000 | 10.7.44.16 | 255.255.255.248 | 10.7.44.17 | 255.255.255.248 |  |  | MEC421 | 10.7.44.18 | MEC105 | 10.7.44.19 | 255.255.255.248 | 10.7.44.17
91 | Upper Belt |  |  | MEC116-MEC105 |  | 2000 | 10.7.44.24 | 255.255.255.248 | 10.7.44.25 | 255.255.255.248 |  |  | MEC116 | 10.7.44.26 | MEC105 | 10.7.44.27 | 255.255.255.248 | 10.7.44.25
92 | Upper Belt |  |  | MEC425-MEC190 |  | 2000 | 10.7.44.32 | 255.255.255.248 | 10.7.44.33 | 255.255.255.248 |  |  | MEC425 | 10.7.44.34 | MEC190 | 10.7.44.35 | 255.255.255.248 | 10.7.44.33
93 | Upper Belt |  |  | MEC126-MEC413 |  | 2000 | 10.7.44.40 | 255.255.255.248 | 10.7.44.41 | 255.255.255.248 |  |  | MEC126 | 10.7.44.42 | MEC413 | 10.7.44.43 | 255.255.255.248 | 10.7.44.41
94 | Upper Belt |  |  | MEC096-MEC413 |  | 2000 | 10.7.44.48 | 255.255.255.248 | 10.7.44.49 | 255.255.255.248 |  |  | MEC096 | 10.7.44.50 | MEC413 | 10.7.44.51 | 255.255.255.248 | 10.7.44.49
95 | Upper Belt |  |  | MEC144-MEC057 |  | 2000 | 10.7.44.56 | 255.255.255.248 | 10.7.44.57 | 255.255.255.248 |  |  | MEC144 | 10.7.44.58 | MEC057 | 10.7.44.59 | 255.255.255.248 | 10.7.44.57
96 | Upper Belt |  |  | BRN044-BRN011 |  | 2000 | 10.7.41.72 | 255.255.255.248 | 10.7.41.73 | 255.255.255.248 |  |  | BRN044 | 10.7.41.74 | BRN011 | 10.7.41.75 | 255.255.255.248 | 10.7.41.73
97 | Upper Belt |  |  | MEC141-MEC158 |  | 2000 | 10.7.40.176 | 255.255.255.248 | 10.7.40.177 | 255.255.255.248 |  |  | MEC141 | 10.7.40.178 | MEC158 | 10.7.40.179 | 255.255.255.248 | 10.7.40.177
98 | Upper Belt |  |  | KOS052_KOS412 |  | 2000 | 10.7.40.184 | 255.255.255.248 | 10.7.40.185 | 255.255.255.248 |  |  | KOS052 | 10.7.40.186 | KOS412 | 10.7.40.187 | 255.255.255.248 | 10.7.40.185
99 | Upper Belt |  |  | KOS283_KOS268 |  | 2000 | 10.7.40.192 | 255.255.255.248 | 10.7.40.193 | 255.255.255.248 |  |  | KOS283 | 10.7.40.194 | KOS268 | 10.7.40.195 | 255.255.255.248 | 10.7.40.193
100 | Upper Belt |  |  | KOS435_KOS149 |  | 2000 | 10.7.40.216 | 255.255.255.248 | 10.7.40.217 | 255.255.255.248 |  |  | KOS435 | 10.7.40.218 | KOS149 | 10.7.40.219 | 255.255.255.248 | 10.7.40.217
101 | Upper Belt |  |  | KOS413-KOS185 |  | 2000 | 10.7.44.64 | 255.255.255.248 | 10.7.44.65 | 255.255.255.248 |  |  | KOS413 | 10.7.44.66 | KOS185 | 10.7.44.67 | 255.255.255.248 | 10.7.44.65
102 | Upper Belt |  |  | BRN045-BRN032 |  | 2000 | 10.7.40.168 | 255.255.255.248 | 10.7.40.169 | 255.255.255.248 |  |  | BRN045 | 10.7.40.170 | BRN032 | 10.7.40.171 | 255.255.255.248 | 10.7.40.169
103 | Upper Belt |  |  | MEC193-MEC425 |  | 2000 | 10.7.47.248 | 255.255.255.248 | 10.7.47.249 | 255.255.255.248 |  |  | MEC193 | 10.7.47.250 | MEC425 | 10.7.47.251 | 255.255.255.248 | 10.7.47.249
104 | Upper Belt |  |  | MEC036-MEC124 |  | 2000 | 10.7.40.160 | 255.255.255.248 | 10.7.40.161 | 255.255.255.248 |  |  | MEC036 | 10.7.40.162 | MEC124 | 10.7.40.163 | 255.255.255.248 | 10.7.40.161
105 | Upper Belt |  |  | KKR002-COW022 |  | 2000 | 10.7.47.240 | 255.255.255.248 | 10.7.47.241 | 255.255.255.248 |  |  | KKR002 | 10.7.47.242 | COW022 | 10.7.47.243 | 255.255.255.248 | 10.7.47.241
106 | Upper Belt |  |  | BPR001-MEC224 |  | 2000 | 10.7.47.232 | 255.255.255.248 | 10.7.47.233 | 255.255.255.248 |  |  | BPR001 | 10.7.47.234 | MEC224 | 10.7.47.235 | 255.255.255.248 | 10.7.47.233
107 | Upper Belt |  |  | KOS283-KOS132 |  | 2000 | 10.7.41.32 | 255.255.255.248 | 10.7.41.33 | 255.255.255.248 |  |  | KOS283 | 10.7.41.34 | KOS132 | 10.7.41.35 | 255.255.255.248 | 10.7.41.33